StyleSnap

Chrome Extension

Implementation Plan  ·  v1.0

Author  Guru (Soham Belwadkar)

Status  Draft v1.0

Date  July 2026

Timeline  12 weeks  —  V1 (Wk 1–3)  ·  V2 (Wk 4–10)  ·  V3 (Wk 11–12)

Companion to  PRD + TRD + Extension Flow + UI/UX + Backend Schema

Product  Omenova Studio

# 1. How to Use This Plan

This document is the single source of truth for building StyleSnap across all three versions. Every task includes a doc reference (which document to consult), the exact file or module to create, and an estimated hour count. Tasks are ordered by dependency — do them top-to-bottom within each week.

| Column | Meaning |
| --- | --- |
| # | Task number — unique identifier across the full plan. Reference as T-001, T-045 etc. |
| Task | What to build. Specific enough to open your editor and start coding. |
| Doc ref | Which companion document and section to read before starting. |
| File / module | Exact file path or module name to create or modify. |
| Hours | Realistic estimate for a developer who knows React + TypeScript but is new to Chrome extensions. |

Version colour coding used throughout this document:

| V1 | V2 | V3 | Each version is independently shippable to the Chrome Web Store. |
| --- | --- | --- | --- |

# 2. Prerequisites & Phase 0 — Environment Setup

Complete Phase 0 before Week 1. These are one-time setup tasks. Estimated total: 3–4 hours.

## 2.1  Accounts & Access

| Account | Purpose | Action |
| --- | --- | --- |
| Google Developer Account | Chrome Web Store publishing | Pay $5 one-time fee at chrome.google.com/webstore/devconsole |
| GitHub account | Version control, portfolio visibility | Create repo: stylesnap-extension (public for portfolio) |
| Chrome browser (latest stable) | Testing environment | Update to latest. Enable Developer Mode in chrome://extensions |
| Chrome Canary (optional) | Test upcoming API changes | Download from google.com/chrome/canary |

## 2.2  Local Environment

| Tool | Version | Install command |
| --- | --- | --- |
| Node.js | 20 LTS | nvm install 20 && nvm use 20 |
| pnpm | 9.x | npm install -g pnpm |
| VS Code | Latest | code.visualstudio.com |
| VS Code extensions | — | ESLint, Prettier, Tailwind CSS IntelliSense, TypeScript Hero |
| Git | 2.x | brew install git (macOS) / apt install git (Linux) |

## 2.3  Phase 0 Task List

| # | Task | Doc ref | File / module | Hours |
| --- | --- | --- | --- | --- |
| P-01 | Create GitHub repo: stylesnap-extension (public). Add MIT licence, .gitignore (Node). | — | github.com/SohamB-ai/stylesnap | 0.5h |
| P-02 | Scaffold project: pnpm create vite@latest stylesnap-extension --template react-ts | TRD §19 | vite.config.ts | 0.5h |
| P-03 | Install core dependencies: pnpm add @crxjs/vite-plugin@2.6.x zustand idb jszip | TRD §2 | package.json | 0.5h |
| P-04 | Install dev dependencies: @types/chrome eslint prettier tailwindcss autoprefixer postcss | TRD §2 | package.json | 0.5h |
| P-05 | Configure vite.config.ts with CRXJS plugin. Reference TRD §19.1 exactly. | TRD §19.1 | vite.config.ts | 0.5h |
| P-06 | Write manifest.config.ts with all V1 permissions (TRD §4.1). Use schemaVersion 1. | TRD §4 | manifest.config.ts | 0.5h |
| P-07 | Set up Tailwind CSS: npx tailwindcss init -p. Configure content paths for sidepanel. | UI/UX §7 | tailwind.config.js | 0.5h |
| P-08 | Create the full folder structure as defined in TRD §3.3. Add index.ts placeholder in each. | TRD §3.3 | src/** | 0.5h |
| P-09 | Copy all TypeScript interfaces from Backend Schema into src/shared/types.ts. | Schema §2–7 | shared/types.ts | 1h |
| P-10 | Copy MessageType enum and all payload types into src/shared/messages.ts. | Schema §10 | shared/messages.ts | 0.5h |
| P-11 | Run pnpm dev. Load dist/ as unpacked extension. Verify panel opens on toolbar click. | — | — | 0.5h |

After P-11: if the side panel does not open, check that chrome.sidePanel.setOptions() is called in background/index.ts onInstalled handler. This is the most common first-launch issue.

# 3. Version 1 — Core Parity  (Weeks 1–3)

Goal: A solid, accurate, free extension that matches everything both reference extensions offer. Ship to Chrome Web Store by end of Week 3. V1 is the foundation all future versions build on — accuracy here matters more than speed.

| V1 Deliverable | Definition of Done |
| --- | --- |
| Token extraction | Colors/typography/spacing/shadows/radii/breakpoints extracted with ≥95% accuracy on 10 test sites |
| Element inspector | Hover → highlight → click → CSS + HTML in panel. Works on 10 test sites. |
| Asset finder | All images/SVGs/icons listed. ZIP download works. Favicon always included. |
| Export formats | DESIGN.md, tokens.json (W3C DTCG), tailwind.config.js — all download correctly. |
| History | Last 10 extractions saved. Load + delete work. Auto-eviction fires on entry 11. |
| CWS listing | Extension live on Chrome Web Store with description, screenshots, privacy policy. |

Week 1  —  Architecture + Service Worker + Side Panel Shell   [V1]

Week 1 Goal: A working extension skeleton — side panel opens, Extract button exists, messaging between panel and SW works. Nothing is extracted yet.

| # | Task | Doc ref | File / module | Hours |
| --- | --- | --- | --- | --- |
| 1-01 | Write background/index.ts service worker entry. Register onInstalled handler — write default settings to chrome.storage.local. | Schema §8.1 Flow §3 | background/index.ts | 1h |
| 1-02 | Implement chrome.sidePanel.setOptions() + chrome.action.onClicked → open side panel. | Flow §4 TRD §4 | background/index.ts | 0.5h |
| 1-03 | Write background/services/db.ts: openStyleSnapDB() with both object stores + all indexes. Match Schema §8.3 exactly. | Schema §8.3 | background/services/db.ts | 1.5h |
| 1-04 | Write background/handlers/extraction.ts stub: receives EXTRACT_PAGE, will call CS (CS not written yet — just log). | Schema §10 | background/handlers/extraction.ts | 0.5h |
| 1-05 | Write background/handlers/export.ts stub: receives EXPORT_FILE, logs payload. | Schema §10 | background/handlers/export.ts | 0.5h |
| 1-06 | Scaffold sidepanel/main.tsx: React 18 createRoot. Mount App. | TRD §3.3 | sidepanel/main.tsx | 0.5h |
| 1-07 | Create sidepanel/store.ts with Zustand. State: ExtractionResult¦null, UIState, theme, settings. | Schema §8.1 UI/UX §7 | sidepanel/store.ts | 1.5h |
| 1-08 | Build Header component: logo, URL display, settings icon. Match UI/UX §3.2. | UI/UX §3.2 | components/Header.tsx | 1h |
| 1-09 | Build TabBar component: Tokens / Assets / History tabs. Active tab state in Zustand. | UI/UX §3.3 | components/TabBar.tsx | 1h |
| 1-10 | Build ActionBar component: Extract button (disabled/loading/idle states) + Export dropdown stub. | UI/UX §3.4 | components/ActionBar.tsx | 1.5h |
| 1-11 | Build EmptyState screen. Match UI/UX §4.1 wireframe. | UI/UX §4.1 | components/EmptyState.tsx | 0.5h |
| 1-12 | Write full CSS custom property theme (dark + light) in sidepanel/index.css. Match UI/UX §7. | UI/UX §7.1 | sidepanel/index.css | 1h |
| 1-13 | Wire EXTRACT_PAGE message: Extract button → chrome.runtime.sendMessage → SW → console.log. Full round-trip verified. | Flow §5 Schema §10 | ActionBar.tsx + SW | 1h |
| 1-14 | Manual test: load extension, open panel on stripe.com, click Extract, confirm message appears in SW console. | — | — | 0.5h |

Week 1 checkpoint: Panel opens, tabs render, Extract button sends a message to SW and you can see it in chrome://extensions → service worker console. Nothing is extracted yet — that is Week 2.

Week 2  —  Token Extraction Engine (Core)   [V1]

Week 2 Goal: Full 3-phase extraction running. ExtractionResult in the panel. Tokens tab rendering real data.

| # | Task | Doc ref | File / module | Hours |
| --- | --- | --- | --- | --- |
| 2-01 | Write content/isolated/index.ts: listens for EXTRACT_PAGE from SW, orchestrates all extraction phases, sends EXTRACTION_PROGRESS over port. | TRD §7 Flow §5 | content/isolated/index.ts | 1h |
| 2-02 | Implement port connection: content script calls chrome.runtime.connect("stylesnap-extraction"). SW listens on onConnect — keeps SW alive during extraction. | TRD §6.2 Flow §5 step 4 | background/index.ts | 1h |
| 2-03 | Write extractor/tokens.ts Phase 1: scanStylesheets(). Iterate document.styleSheets, extract CSS custom properties from :root and *, extract @media breakpoints. Match TRD §7.1 code exactly. | TRD §7.1 | content/isolated/extractor/tokens.ts | 2h |
| 2-04 | Write Phase 2: walkDOM(). Iterate up to 2000 visible elements. getComputedStyle() for colors (5 properties), fonts (family/size/weight/lineHeight), spacings (8 properties), radii, shadows. Match TRD §7.2. | TRD §7.2 | content/isolated/extractor/tokens.ts | 3h |
| 2-05 | DECISION POINT: Set color clustering tolerance to ±5°/10%/10% as recommended in TRD §21. Document this decision in code comment for easy adjustment. | TRD §21 | extractor/tokens.ts | — |
| 2-06 | Write Phase 3: deduplicate and normalize. Color clustering (HSL proximity), type scale sorting and role labeling (h1–h6/body/caption), spacing grid detection (4px base), shadow elevation classification, radius level naming. | TRD §7.3 | extractor/tokens.ts | 3h |
| 2-07 | Write framework detection: check for Tailwind utility classes (bg-*, text-*, p-*), styled-components (<style data-styled>), Emotion (<style data-emotion>), CSS variables (:root --var). Set FrameworkType. | TRD §7.4 Schema §2 | extractor/tokens.ts | 1.5h |
| 2-08 | Write extractor/assets.ts: scan img, svg, picture, CSS background-image, favicon. Build AssetManifest. Match Schema §7 types exactly. | TRD §9 Schema §7 | content/isolated/extractor/assets.ts | 2h |
| 2-09 | Assemble ExtractionResult in content script. Send EXTRACTION_COMPLETE to SW via port. | Schema §2 | content/isolated/index.ts | 1h |
| 2-10 | SW handler: receive EXTRACTION_COMPLETE. Call saveExtraction() from db.ts — write to IndexedDB + update history. Match Schema §9.1 exactly (including eviction logic). | Schema §9.1 | background/handlers/extraction.ts | 2h |
| 2-11 | SW forwards ExtractionResult to side panel via chrome.runtime.sendMessage. Panel receives and updates Zustand store. | Flow §5 step 16–18 | background/handlers/extraction.ts | 0.5h |
| 2-12 | Build TokensTab.tsx: colour swatches grid, typography specimen, spacing visualiser, shadow/radius/breakpoint rows. All values from Zustand store. Match UI/UX §4.3 wireframe. | UI/UX §4.3 UI/UX §5.2 | sidepanel/components/TokensTab.tsx | 3h |
| 2-13 | Implement copy-to-clipboard on every token value. 3-state copy button (default → copied → reset). Match UI/UX §6.1 exactly. | UI/UX §6.1 | components/CopyButton.tsx | 1h |
| 2-14 | Build ExtractingState.tsx: progress bar (4px, animated fill), step label, skeleton rows. Match UI/UX §4.2. | UI/UX §4.2 | components/ExtractingState.tsx | 1h |
| 2-15 | Accuracy test: run extraction on stripe.com, linear.app, vercel.com. Manually compare tokens to DevTools. Fix any >5% error. Document results. | TRD §20.2 | — | 2h |

Week 2 checkpoint: Extract Full Page on stripe.com returns the correct primary indigo (#635BFF) as the top color, Inter as the primary font, and the correct spacing scale. Screenshots the panel and save for the portfolio case study.

Week 3  —  Inspector + Assets + Exports + History + CWS V1   [V1]

Week 3 Goal: All V1 features complete. Extension published on Chrome Web Store.

| # | Task | Doc ref | File / module | Hours |
| --- | --- | --- | --- | --- |
| 3-01 | Write content/isolated/inspector.ts: inject overlay div, attach mouseover + click listeners (capture phase). getComputedStyle on click, extractRelevantCSS (diff from baseline). Send ELEMENT_SELECTED. | TRD §8 Flow §6 | content/isolated/inspector.ts | 2.5h |
| 3-02 | Handle INSPECT_ACTIVATE / INSPECT_DEACTIVATE messages in content script. Wire Inspect button in panel. | Flow §6 | content/isolated/index.ts | 0.5h |
| 3-03 | Build ElementSelectedView in panel: tag badge, formatted CSS block (syntax highlight key props), HTML snippet, Copy All CSS + Copy HTML buttons, Inspect Again + Done. | UI/UX §4.9 | components/ElementSelected.tsx | 2h |
| 3-04 | Build AssetsTab.tsx: 4-column grid, type filter bar, individual Copy URL + Copy Data URI per card, favicon row at top. Match UI/UX §4.5. | UI/UX §4.5 UI/UX §5.6 | components/AssetsTab.tsx | 2h |
| 3-05 | Implement asset ZIP download: JSZip, fetch each asset URL in SW context, folder structure as Schema §12.2. chrome.downloads.download(). | Schema §12.2 | background/handlers/export.ts | 2h |
| 3-06 | Implement DESIGN.md generator. Match Schema §11.2 template exactly. All sections included. | Schema §11.2 | background/services/exporter.ts | 1.5h |
| 3-07 | Implement tokens.json generator. W3C DTCG 2025.10 format. Match Schema §11.1 template. | Schema §11.1 | background/services/exporter.ts | 1h |
| 3-08 | Implement tailwind.config.js generator. Skip default Tailwind values (use a lookup table). Match Schema §11.3. | Schema §11.3 | background/services/exporter.ts | 1.5h |
| 3-09 | Build Export dropdown in ActionBar: DESIGN.md / tokens.json / tailwind.config.js + Copy DESIGN.md to Clipboard. Wire to EXPORT_FILE message. | UI/UX §5.9 Flow §8 | components/ActionBar.tsx | 1.5h |
| 3-10 | Build HistoryTab.tsx: entry list (favicon, title, URL, timestamp, counts, delete icon). Click → HISTORY_LOAD → load ExtractionResult from IndexedDB → populate store. | UI/UX §4.7 Flow §9 | components/HistoryTab.tsx | 2h |
| 3-11 | Implement HISTORY_DELETE in SW. Cascade delete: ExtractionRecord + ScreenshotRecord (if any). Match Schema §9.2 exactly. | Schema §9.2 Flow §9.2 | background/services/db.ts | 1h |
| 3-12 | Build SettingsPanel.tsx: theme radio (dark/light/system), default format selector, DOM sample limit input, Clear all history button. Slide-in from right. | UI/UX §4.8 | components/SettingsPanel.tsx | 2h |
| 3-13 | Implement theme switching: set data-theme on :root, persist to chrome.storage.local. System preference detection (prefers-color-scheme media query). Match UI/UX §7.2. | UI/UX §7.2 | sidepanel/store.ts | 1h |
| 3-14 | Build all error states: extraction failed, restricted page, extraction interrupted with retry. Match UI/UX §4.10. | UI/UX §4.10 | components/ErrorState.tsx | 1h |
| 3-15 | Build Toast notification component: slide-up 200ms, auto-dismiss 3s, success/error variants. Match UI/UX §5.7 + §8. | UI/UX §5.7 | components/Toast.tsx | 1h |
| 3-16 | Add all ARIA labels (role, aria-label, aria-describedby) to interactive elements. Match UI/UX §9.2. | UI/UX §9.2 | All components | 1h |
| 3-17 | Full end-to-end test: 10 reference sites (Schema §14 list). Fix accuracy issues. Target ≥95%. | TRD §20 | — | 2h |
| 3-18 | Write privacy policy (1 page). Host on GitHub Pages or Vercel. URL needed for CWS listing. | — | privacy-policy.html | 0.5h |
| 3-19 | Create CWS store assets: 3 screenshots (1280×800), 1 promotional tile (440×280). Record a 30-second demo GIF. | — | assets/cws/ | 2h |
| 3-20 | Publish V1 to Chrome Web Store. Fill description, category (Developer Tools), privacy policy URL. Submit for review. | — | chrome.google.com/webstore/devconsole | 1h |

CWS review typically takes 1–3 business days for a new extension. While waiting for approval, begin V2 scaffolding. If rejected, the most common reasons are: overly broad host_permissions without justification, or missing privacy policy. Both are easy fixes.

# 4. Version 2 — Upgraded Accuracy & Depth  (Weeks 4–10)

Goal: Introduce features that neither competitor has — layout extraction, component detection, AI prompt engine, and screenshot pipeline. V2 is the version that makes StyleSnap a genuinely differentiated product.

| V2 Deliverable | Definition of Done |
| --- | --- |
| Screenshot pipeline | Full-page PNG + section screenshots captured and downloadable for any typical webpage. |
| Layout extraction | Section breakdown with grid/flex info for any of the 10 reference sites. |
| Component detection | ≥10 components detected with ≥90% label accuracy on component-heavy sites (e.g., stripe.com). |
| AI prompt engine | 5 tool-specific master prompts generated. Developer can paste Cursor prompt into Cursor and get correct UI. |
| Edge case handling | Tailwind-heavy, CSS-in-JS, and CSS-variable sites all extract with ≥97% accuracy. |
| CWS update | V2 published as an update to the existing CWS listing. |

Week 4  —  Screenshot Pipeline   [V2]

| # | Task | Doc ref | File / module | Hours |
| --- | --- | --- | --- | --- |
| 4-01 | Request unlimitedStorage optional permission at V2 first launch (detect via Settings.schemaVersion). Show panel notification before triggering permission dialog. Match Schema §14.3. | Schema §14.3 | background/index.ts | 1h |
| 4-02 | Write screenshot capture in SW: CAPTURE_SCREENSHOT → chrome.tabs.captureVisibleTab(null, { format:"png" }) → return dataUrl. | TRD §10 Flow §11 | background/handlers/screenshot.ts | 1h |
| 4-03 | Write scroll-and-stitch in content script: record dimensions, hide sticky elements, disable smooth-scroll, tile loop (150ms settle, 50-tile cap), restore page state, send STITCH_TILES. Match TRD §10.1 exactly. | TRD §10.1 Flow §11.1 | content/isolated/extractor/screenshot.ts | 3h |
| 4-04 | DECISION POINT: Use side panel canvas (not OffscreenCanvas in SW). Implement stitchTiles() in a React hook in the panel. Match TRD §21 recommendation. | TRD §21 | sidepanel/hooks/useStitch.ts | — |
| 4-05 | Implement stitchTiles() in panel: create canvas, drawImage each tile at correct y offset, handle partial last tile with clip. Match TRD §10.2. | TRD §10.2 Flow §11.2 | sidepanel/hooks/useStitch.ts | 2h |
| 4-06 | Write screenshot storage: canvas.toBlob() → send STORE_SCREENSHOT to SW → db.put("screenshots", record). | Schema §8.2 Flow §11.2 | background/services/db.ts | 1h |
| 4-07 | Handle edge cases: infinite scroll (stop when scrollHeight stops increasing), sticky element detection (position:sticky/fixed), max 50 tiles safety limit. Match TRD §10.3. | TRD §10.3 | content/isolated/extractor/screenshot.ts | 1.5h |
| 4-08 | Add screenshots ZIP folder to generateFullZIP() in exporter.ts. Match Schema §12.1 folder structure. | Schema §12.1 | background/services/exporter.ts | 1h |
| 4-09 | Test screenshot pipeline on 5 sites: stripe.com, linear.app, vercel.com, a Webflow site, a parallax scroll site. Fix stitching artifacts. | TRD §10.3 | — | 2h |

Week 5  —  Layout Structure Extraction   [V2]

| # | Task | Doc ref | File / module | Hours |
| --- | --- | --- | --- | --- |
| 5-01 | Write extractor/layout.ts: detect semantic landmarks (<header>, <nav>, <main>, <footer>, <section>) using querySelectorAll. | TRD §15 Schema §5 | content/isolated/extractor/layout.ts | 1.5h |
| 5-02 | For non-semantic sections: find large divs (width > 80% viewport, height > 200px) not already captured by landmarks. | TRD §15.1 | content/isolated/extractor/layout.ts | 1h |
| 5-03 | For each section: read display, grid-template-columns, flex-direction, gap, align-items, justify-content, padding, backgroundColor, minHeight via getComputedStyle. | Schema §5 | content/isolated/extractor/layout.ts | 1h |
| 5-04 | Label each section: apply heuristics (header+nav → "navigation", large section+h1+button → "hero", grid of 3+ similar children → "features", etc.) | Schema §5 SectionLabel type | content/isolated/extractor/layout.ts | 1.5h |
| 5-05 | Detect base grid: find widest container element, read grid-template-columns and gap. Set GridInfo in LayoutStructure. | Schema §5 GridInfo | content/isolated/extractor/layout.ts | 1h |
| 5-06 | Append LayoutStructure to ExtractionResult. Update saveExtraction() to persist it. | Schema §2 | content/isolated/index.ts | 0.5h |
| 5-07 | Add layout section info to DESIGN.md generator — insert "## Page Layout" section with grid info + sections table. | Schema §11.2 | background/services/exporter.ts | 1h |

Week 6–7  —  Component Detection Engine   [V2]

This is the highest-effort V2 task — budget 2 full weeks. The component detection algorithm is where StyleSnap's portfolio value lives.

| # | Task | Doc ref | File / module | Hours |
| --- | --- | --- | --- | --- |
| 6-01 | Write extractor/components.ts. Signal 1: Semantic HTML scan — querySelectorAll("button, nav, input, form, header, footer, dialog, select"). Assign base score 0.35 per instance. | TRD §11.1 Schema §4 | content/isolated/extractor/components.ts | 1h |
| 6-02 | Signal 2: ARIA role scan — querySelectorAll("[role]"). Add 0.25 to score for elements with role attribute. | TRD §11.1 | content/isolated/extractor/components.ts | 0.5h |
| 6-03 | Signal 3: Repeated structure scan. Implement getStructureSignature() — recursive tag+child fingerprint. Match TRD §11.3 code exactly. | TRD §11.3 | content/isolated/extractor/components.ts | 2h |
| 6-04 | DECISION POINT: Set component DOM sample limit to 1500 elements (TRD §21). Make it configurable via Settings.domSampleLimit (future). | TRD §21 | content/isolated/extractor/components.ts | — |
| 6-05 | Run getStructureSignature() on all elements with 2+ children (up to 1500). Group by signature. Find patterns with ≥3 instances → add 0.25 score. | TRD §11.3 | content/isolated/extractor/components.ts | 1h |
| 6-06 | Signal 4: Class name heuristic — check element.className for "btn", "card", "modal", "badge", "chip", "hero", "avatar", "nav". Add 0.15 if matched. | TRD §11.1 | content/isolated/extractor/components.ts | 0.5h |
| 6-07 | Merge all signals per element. Calculate total confidence. Filter: ≥0.60 → confirmed, 0.45–0.59 → uncertain, <0.45 → discard. Deduplicate multi-signal detections. | TRD §11.2 | content/isolated/extractor/components.ts | 1h |
| 6-08 | For each confirmed component: extract outerHTML (≤4KB, text truncated to 80 chars, src → placeholder), derive scoped CSS block (non-default computed styles for element + children). | TRD §11.4 Schema §4 | content/isolated/extractor/components.ts | 2h |
| 6-09 | Build ComponentsTab.tsx: component cards grid (label, confidence dot, instance count, HTML/CSS preview, Copy HTML + Copy CSS). Collapsed uncertain section. Match UI/UX §4.4. | UI/UX §4.4 UI/UX §5.5 | sidepanel/components/ComponentsTab.tsx | 3h |
| 6-10 | Implement manual promote/dismiss for uncertain components in panel (user can add uncertain → confirmed list, or hide it). | UI/UX §4.4 | sidepanel/components/ComponentsTab.tsx | 1h |
| 7-01 | Implement components.md generator. Match Schema §11.4 template exactly — HTML + CSS per component, uncertain section at bottom. | Schema §11.4 | background/services/exporter.ts | 1.5h |
| 7-02 | Add "Download components.md" button to ComponentsTab. | UI/UX §4.4 | components/ComponentsTab.tsx | 0.5h |
| 7-03 | Add components.md to generateFullZIP() output. | Schema §12.1 | background/services/exporter.ts | 0.5h |
| 7-04 | Accuracy test: run component detection on stripe.com, linear.app, chakra-ui.com docs. Compare detected components to manually identified list. Target ≥10 components, ≥90% label accuracy. | TRD §20 | — | 2h |
| 7-05 | Tune false positive handling: if a detected "component" is actually a nav item or a text span, adjust scoring thresholds. Re-test. Document final thresholds in code comments. | TRD §11.2 | extractor/components.ts | 2h |

Week 8  —  AI Prompt Generation Engine   [V2]

| # | Task | Doc ref | File / module | Hours |
| --- | --- | --- | --- | --- |
| 8-01 | Write 5 prompt templates in background/services/promptTemplates.ts: cursor, claude-code, v0, bolt, lovable. Match Schema §11.5 token budget constraints. | Schema §11.5 | background/services/promptTemplates.ts | 2h |
| 8-02 | Write generateMasterPrompt(result, tool): inject ExtractionResult data into selected template. Token count estimation (rough: chars/4). | Schema §11.5 | background/services/exporter.ts | 1.5h |
| 8-03 | Build AIPromptTab.tsx: tool selector dropdown (5 tools), prompt preview textarea (read-only, monospace), token count badge (amber if >2000), Copy Prompt + Download .txt buttons. Match UI/UX §4.6. | UI/UX §4.6 | sidepanel/components/AIPromptTab.tsx | 2.5h |
| 8-04 | Wire tool selector → instant prompt regeneration (synchronous in panel, <100ms). No SW call for generation. | UI/UX §4.6 Flow §13 | sidepanel/components/AIPromptTab.tsx | 0.5h |
| 8-05 | Add master prompt files to generateFullZIP() — one .txt per tool: master-prompt-cursor.txt etc. Match Schema §12.1. | Schema §12.1 | background/services/exporter.ts | 0.5h |
| 8-06 | Integration test: generate Cursor prompt from stripe.com extraction. Paste into a Cursor project. Verify it produces correct indigo-branded UI without additional prompting. | Schema §11.5 | — | 1.5h |
| 8-07 | Add Components tab to TabBar. Add AI Prompt tab. Both visible in V2 build only (check version in manifest). | UI/UX §3.3 | sidepanel/components/TabBar.tsx | 0.5h |

Week 9–10  —  Edge Cases + CSS-in-JS + Polish + CWS V2   [V2]

| # | Task | Doc ref | File / module | Hours |
| --- | --- | --- | --- | --- |
| 9-01 | DECISION POINT: Tailwind v4 CSS-first format. Detect @theme block in stylesheets. If found, generate both tailwind.config.js (v3) AND @theme CSS block (v4). Match TRD §21. | TRD §21 | background/services/exporter.ts | — |
| 9-02 | Implement Tailwind v4 @theme CSS generator as additional export option. | Schema §11.3 TRD §21 | background/services/exporter.ts | 1.5h |
| 9-03 | Improve CSS-in-JS handling: detect styled-components/Emotion, show warning in panel, add note to exports: "Framework detected: CSS-in-JS. Token extraction uses computed styles (ground truth)." | TRD §7.4 | extractor/tokens.ts + panel | 1h |
| 9-04 | Handle iframes: detect cross-origin iframes in asset finder. List them as "iframe (cross-origin — cannot extract)" in the assets panel. | TRD §10.3 | extractor/assets.ts | 0.5h |
| 9-05 | Handle port disconnect during long operations: save checkpoint to chrome.storage.session on every EXTRACTION_PROGRESS event. Implement retry-from-checkpoint on reconnect. | TRD §5.4 Flow §17.3 | background/handlers/extraction.ts | 2h |
| 9-06 | Add schema migration for V2: Settings schemaVersion 1→2. Add defaultAITool field. openDB() version 1→2 (add screenshots store). Match Schema §13. | Schema §13 | background/services/db.ts | 1h |
| 9-07 | Full accuracy audit on 10 reference sites with V2 feature set. Target: tokens ≥97%, components ≥90%, layout labels correct. Fix regressions. | TRD §20 | — | 3h |
| 9-08 | Keyboard navigation audit: tab through full panel, verify focus rings visible, all dropdowns keyboard-accessible, Escape closes settings. Match UI/UX §9.3. | UI/UX §9.3 | All components | 1.5h |
| 9-09 | Responsive panel audit: resize panel to 280px, verify tab icons-only mode, verify Export dropdown truncates cleanly. Match UI/UX §10.1. | UI/UX §10.1 | All components | 1h |
| 10-01 | Write V2 release notes for CWS update. Update description to mention layout, components, AI prompts, screenshots. | — | — | 0.5h |
| 10-02 | Create 3 new CWS screenshots showing Components tab, AI Prompt tab, screenshot export. | — | assets/cws/v2/ | 1.5h |
| 10-03 | Update promotional tile (440×280) with V2 feature highlights. | — | assets/cws/v2/ | 0.5h |
| 10-04 | Bump version to 2.0.0. Rebuild. Publish V2 update to Chrome Web Store. | — | manifest.config.ts | 0.5h |
| 10-05 | Write V2 portfolio case study entry: component detection algorithm decisions, false positive rate before/after tuning, screenshot stitching challenges. Publish to portfolio site. | — | sohamisonline.vercel.app | 2h |

# 5. Version 3 — Extreme Features  (Weeks 11–12)

Goal: Add the one feature no competitor has — animation and scroll-effect detection. V3 is the technical showpiece of the portfolio. The MAIN world injection and multi-library detection algorithm are the most technically impressive parts of the entire project.

| V3 Deliverable | Definition of Done |
| --- | --- |
| Animation detection | GSAP/ScrollTrigger, AOS, Lenis, Locomotive Scroll, ScrollMagic all detected with ≥90% recall on 10 known sites. |
| Three.js/WebGL detection | Presence detected and reported. Version + draw call stats shown. |
| Written descriptions | Every detected library produces a human-readable description included in all export formats. |
| CSP fallback | Graceful fallback to DOM-only detection when MAIN world injection blocked. |
| CWS V3 update | V3 published. All 3 versions documented in case study. |

Week 11  —  Animation & Scroll Detection Engine   [V3]

| # | Task | Doc ref | File / module | Hours |
| --- | --- | --- | --- | --- |
| 11-01 | Write content/main-world/animation.ts: the MAIN world script. Add it to web_accessible_resources in manifest.config.ts. This file cannot use chrome.* APIs. | TRD §13.1 Flow §14.1 | content/main-world/animation.ts | 0.5h |
| 11-02 | Implement MAIN world injection in SW: chrome.scripting.executeScript({ files:["animation.js"], world:"MAIN" }). Wire to DETECT_ANIMATIONS message. | Flow §14.1 step 2 | background/handlers/extraction.ts | 0.5h |
| 11-03 | In ISOLATED content script: attach window.addEventListener("message") to listen for { source:"stylesnap-main" }. Forward AnimationReport to SW. | Flow §14.1 step 3 | content/isolated/index.ts | 0.5h |
| 11-04 | GSAP detection: check window.gsap. If present: read window.gsap.version. Read ScrollTrigger.getAll() — extract start, end, scrub, pin, toggleClass, ease per trigger. Build GSAPConfig. Match Schema §6. | Schema §6 TRD §13.2 | content/main-world/animation.ts | 2h |
| 11-05 | AOS detection: check window.AOS. Read window.AOS.options. QuerySelectorAll("[data-aos]") — extract animation, duration, delay, easing, offset per element. Group identical combos. Build AOSConfig. | Schema §6 TRD §13.2 | content/main-world/animation.ts | 1.5h |
| 11-06 | Lenis detection: check window.lenis. Read lenis.options: duration, easing, smoothWheel, infinite. Build LenisConfig. | Schema §6 TRD §13.2 | content/main-world/animation.ts | 0.5h |
| 11-07 | Locomotive Scroll detection: check window.LocomotiveScroll. QuerySelectorAll("[data-scroll]") — extract speed, direction, delay. Build LocomotiveConfig. | Schema §6 TRD §13.2 | content/main-world/animation.ts | 1h |
| 11-08 | ScrollMagic detection: check window.ScrollMagic. Framer Motion detection: check window.motion / window.__framer_importedPackages. Three.js: check window.THREE — read revision, canvas count, WebGL version. | Schema §6 TRD §13.2 | content/main-world/animation.ts | 1.5h |
| 11-09 | Vanilla scroll heuristic (Tier 3): check for IntersectionObserver usage (document.querySelectorAll("[data-inview]") etc.), CSS transition/animation properties on body children. | TRD §13.2 | content/main-world/animation.ts | 1h |
| 11-10 | Assemble AnimationReport from all library results. Assign accuracy tier to each library. Write human-readable description string per library. Post via window.postMessage({ source:"stylesnap-main" }). | Schema §6 Flow §14.1 step 11 | content/main-world/animation.ts | 1.5h |
| 11-11 | Implement 3-second timeout: if no postMessage received after injection, ISOLATED script fires ANIMATION_TIMEOUT to SW. SW notifies panel with non-blocking error notice. | Flow §14.3 E2 | content/isolated/index.ts | 0.5h |
| 11-12 | Implement CSP fallback in SW: if executeScript throws, send DETECT_ANIMATIONS_DOM_ONLY to CS. CS runs attribute-only scan (data-aos, data-scroll, data-animation). Sets tier to Tier 3. | Flow §14.3 E1 | background/handlers/extraction.ts | 1h |
| 11-13 | Add animation section to DESIGN.md generator. Add AnimationReport to all master prompt generators (after components section). | Schema §11.2 §11.5 | background/services/exporter.ts | 1h |
| 11-14 | Detection accuracy test: run on 5 known GSAP sites (e.g. awwwards nominees), 3 AOS sites, 2 Lenis sites. Target ≥90% recall. Fix missed detections. | TRD §20 | — | 2h |

Week 12  —  UI + Portfolio + Final Polish + CWS V3   [V3]

| # | Task | Doc ref | File / module | Hours |
| --- | --- | --- | --- | --- |
| 12-01 | Build animation section in TokensTab: detected library badges (green pills), expandable trigger detail accordions, accuracy tier label per library, "No animations detected" empty state. | UI/UX §4.3 Flow §14.2 | sidepanel/components/TokensTab.tsx | 2h |
| 12-02 | Add animation info to AI Prompt tab: include AnimationReport.summary in all prompt previews. Regenerate when extraction changes. | UI/UX §4.6 | sidepanel/components/AIPromptTab.tsx | 1h |
| 12-03 | Add schema migration V3: Settings schemaVersion 2→3. Add enableAnimationDetection field (default true). Match Schema §13. | Schema §13 | background/services/db.ts | 0.5h |
| 12-04 | Full 12-site accuracy audit (V1+V2+V3 features together). Fix regressions introduced by V3 changes. Document final accuracy numbers. | TRD §20 | — | 2h |
| 12-05 | Performance audit: time token extraction on a 5MB page (< 3s target). Time component detection (< 5s). Time animation detection (< 500ms). Optimise anything above threshold. | TRD §17 | — | 1.5h |
| 12-06 | Final keyboard + accessibility audit. Verify all ARIA labels present. Verify reduced-motion preference disables all transitions. | UI/UX §9 | — | 1h |
| 12-07 | Write comprehensive README.md: what the extension does, screenshots, features per version, tech stack, how to build and load locally, contribution guide. | — | README.md | 1.5h |
| 12-08 | Write full portfolio case study (all 3 versions): problem → research → architecture decisions (component detection algorithm, MAIN world injection, per-tool prompt tuning) → challenges → results (accuracy %, install count). Publish to portfolio. | — | sohamisonline.vercel.app | 3h |
| 12-09 | Create 3 new CWS screenshots showing animation detection output. Update promotional tile. | — | assets/cws/v3/ | 1.5h |
| 12-10 | Bump version to 3.0.0. Rebuild. Publish V3 update to Chrome Web Store. Write public release notes. | — | manifest.config.ts | 0.5h |
| 12-11 | Share on Twitter/X, IndieHackers, Reddit (r/webdev, r/chrome_extensions). Write a dev.to article about the animation detection architecture. Link to CWS listing. | — | — | 2h |

# 6. Open Decision Resolution Schedule

Four technical decisions were flagged as unresolved in the TRD (§21). Each has a mandatory resolution point in this plan. Do not proceed past the decision week without resolving it.

| # | Decision | Resolve by | Task ref | Recommendation |
| --- | --- | --- | --- | --- |
| D-01 |  |
| D-02 |  |
| D-03 |  |
| D-04 |  |

# 7. Testing Milestones

## 7.1  Reference Test Sites

These 12 sites are used throughout the plan for accuracy audits. Each covers a different CSS authoring pattern.

| Site | Framework | Tests | First used |
| --- | --- | --- | --- |
| stripe.com | Vanilla CSS + variables | Colors, typography, components | Week 2 |
| linear.app | CSS variables | Design system tokens | Week 2 |
| vercel.com | CSS variables + Tailwind | Mixed framework handling | Week 2 |
| tailwindcss.com | Tailwind v3 | Tailwind utility detection | Week 2 |
| railway.app | Tailwind | Tailwind accuracy | Week 2 |
| chakra-ui.com docs | Emotion (CSS-in-JS) | CSS-in-JS fallback | Week 3 |
| resend.com | Tailwind | Component detection | Week 7 |
| framer.com | Framer Motion | Animation detection | Week 11 |
| awwwards.com nominee (any) | GSAP + ScrollTrigger | GSAP detection accuracy | Week 11 |
| lenis.darkroom.engineering | Lenis smooth scroll | Lenis detection | Week 11 |
| michalsnik.github.io/aos | AOS library | AOS detection | Week 11 |
| threejs.org | Three.js / WebGL | Three.js presence | Week 12 |

## 7.2  Accuracy Targets Per Version

| Metric | V1 target | V2 target | V3 target |
| --- | --- | --- | --- |
| Token extraction accuracy (manual audit) | ≥95% | ≥97% | ≥98% |
| Component label accuracy (on 5 sites) | N/A | ≥90% | ≥90% |
| Animation library detection recall (10 known sites) | N/A | N/A | ≥90% |
| Full-page screenshot accuracy (no artifacts) | N/A | ≥80% of test sites | ≥80% |
| Export format validity (parseable JSON, valid JS) | 100% | 100% | 100% |
| Panel load time | <200ms | <200ms | <200ms |
| Extraction time (typical page) | <3s | <5s | <6s |

# 8. Chrome Web Store Submission Checklists

## 8.1  V1 Submission (end of Week 3)

- Extension icon: 16px, 32px, 48px, 128px PNG versions (no transparency issues)

- Promotional tile: 440×280px PNG (required for featured listing)

- Store screenshots: minimum 1, maximum 5. Use 1280×800px. Show: empty state, tokens tab, asset tab, export.

- Short description: ≤132 characters. Draft: "Extract any website's design system in one click — colours, fonts, spacing, components, and AI-ready prompts."

- Detailed description: explain all V1 features, mention zero backend / privacy-first, link to GitHub repo

- Category: Developer Tools

- Language: English

- Privacy policy URL: hosted page stating no user data is collected or transmitted

- Permissions justification: each permission listed with clear justification (CWS requires this for tabs permission)

- Single purpose description: "Extract and export design systems from any website"

- Run pnpm build, zip the dist/ folder, upload the ZIP

- Test the uploaded version in a clean Chrome profile before submitting

The "tabs" permission (for captureVisibleTab) requires explicit justification in the CWS submission form. Write: "Required to capture screenshots of the current page for the screenshot export feature." Failing to justify this is the #1 cause of new extension rejections.

## 8.2  V2 Update (end of Week 10)

- Bump version to 2.0.0 in manifest.config.ts

- Request unlimitedStorage as optional permission (not required — user is prompted at runtime)

- Add 3 new screenshots showing Components tab, AI Prompt tab, screenshot export

- Update store description to mention layout, components, AI prompts (Cursor/Claude Code/v0/Bolt/Lovable), screenshots

- Write What's New text (≤500 chars) for the CWS update

- Test migration: install V1, extract a page, update to V2, verify history entry still loads correctly

## 8.3  V3 Update (end of Week 12)

- Bump version to 3.0.0

- Add animation.js to web_accessible_resources (already in manifest from V3 Week 11)

- Add 3 new screenshots showing animation detection output for a GSAP-heavy site

- Update store description to highlight animation/scroll detection as the headline V3 feature

- Write What's New text: "V3: Detect GSAP, AOS, Lenis, Locomotive Scroll, ScrollMagic, Framer Motion, and Three.js on any page."

- Test MAIN world injection on 5 different animation sites before submitting

# 9. Portfolio Documentation Guide

StyleSnap is a deep portfolio piece. Document it thoroughly during the build — not after. The case study is what gets you clients and interviews, not the extension itself.

## 9.1  What to Capture During Build

- Week 2: Screenshot the panel showing stripe.com extraction result. This is your hero image.

- Week 6–7: Record a GIF of component detection running on a real site (card + button + nav detected). This demonstrates the most impressive algorithm.

- Week 11: Record the animation detection output on a GSAP ScrollTrigger-heavy site — show the trigger list with start/end/scrub values. This is uniquely impressive.

- Every version: note the exact accuracy numbers from your audit. Real numbers (e.g. "94.7% color accuracy before tuning, 97.2% after") are far more convincing than vague claims.

- Note every technical challenge and how you solved it — false positive rate in component detection, sticky element artifacts in screenshots, CSP fallback for animation detection.

## 9.2  Case Study Structure

| Section | Content |
| --- | --- |
| Problem | Screenshot of the gap in existing tools. Competitor comparison table from PRD §2.2. |
| Research | What you found in Design System Extractor + DESIGN.md. Why neither was sufficient. |
| Architecture | Four-context model diagram (from Extension Flow §2). Why MAIN world is needed for animations. |
| Technical deep-dive #1 | Component detection algorithm: structure signatures, confidence scoring, false positive tuning. |
| Technical deep-dive #2 | Animation detection: MAIN world injection, per-library globals, accuracy tiers. |
| Results | CWS install count, accuracy numbers, demo GIF. Screenshots of output on 3 real sites. |
| What I learned | Chrome extension MV3 constraints, getComputedStyle performance, prompt engineering for different AI tools. |

## 9.3  Where to Publish

- sohamisonline.vercel.app — primary portfolio (add project card with hero screenshot)

- github.com/SohamB-ai/stylesnap-extension — public repo with detailed README

- dev.to — technical article about the animation detection architecture (drives organic traffic)

- Twitter/X thread — 5-tweet thread with GIF demos at each version ship (V1, V2, V3)

# 10. Risk Register

| Risk | Version | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| Component detection produces too many false positives on complex sites |  |
| CWS rejects extension for "tabs" permission |  |
| MAIN world injection blocked on specific sites (CSP) |  |
| Service worker terminates mid-extraction |  |
| Screenshot stitching produces artifacts on parallax/sticky sites |  |
| Tailwind utility class detection misidentifies design tokens |  |
| IndexedDB quota exceeded before unlimitedStorage granted |  |
| GSAP site does not expose window.gsap (bundled without global) |  |

# 11. Full Timeline at a Glance

| Week | Version | Theme | Key deliverable |
| --- | --- | --- | --- |
| Phase 0 |  |
| Week 1 |  |
| Week 2 |  |
| Week 3 |  |
| Week 4 |  |
| Week 5 |  |
| Weeks 6–7 |  |
| Week 8 |  |
| Weeks 9–10 |  |
| Week 11 |  |
| Week 12 |  |

# 12. Document History

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| v1.0 | July 2026 | Guru (Soham Belwadkar) | Initial plan — Phase 0 + 12 weeks + open decisions + CWS checklists + portfolio guide + risk register |